## Slide 1
City of La Crosse & La Crosse County
Creating a Long-Term Homelessness Response Plan Covering the City of La Crosse
Project Management Plan
Updated as of August 24, 2023
Summary

## Slide 2
City of La Crosse & La Crosse County
Creating a Long-Term Homelessness Response Plan Covering the City of La Crosse
PROJECT PHASES
PLANNING
IMPLEMENTATION
MAINTENANCE
PHASE #1
(2023)
PHASE #2
(2024)
Dec 31st
Dec 31st
(2025)
PHASE #3

## Slide 3
City of La Crosse & La Crosse County
1.
Select
a Design Process
2.
Create
a Stakeholder Engagement Blueprint
3.
Execute
Design Process & Engagement Blueprint
4.
Draft
a Written 5-Year Homelessness Response Plan*
Creating a Long-Term Homelessness Response Plan Covering the City of La Crosse
5.
Prepare
a Presentation & Communication Blueprint
PLANNING PHASE: COORDINATION & KEY MILESTONES
Key Milestones
Coordination
City / County Coordinating Team | City / County Coordinating Team
PARTICIPANTS: | Brian Sampson Alexia Krause Andrea Trane Isaac Hoffman Jason Witt
RESOURCES: | Project Management: John Parshall Fiscal Mapping / Analysis: Jen Vote
SCOPE: | - Create & Oversee Project Management Plan - Coordinate Ongoing Workstreams - Troubleshoot Day to Day Issues - Finalize homeless response plan and advance it to the Mayor & County Administrator
* To include recommendations with regards to financing

## Slide 4
City of La Crosse & La Crosse County
Creating a Long-Term Homelessness Response Plan Covering the City of La Crosse
DESIGN PROCESS: “Circle, Arrow, Circle”
(July 1, 2023 – December 31, 2023)
CURRENT
STATE
FUTURE
STATE
#1
Primary work completed by: Oct 1st
Align on understanding of how the homeless response system currently functions
Map the current system
Identify barriers and opportunities within the current state
#2
Untethered from current state thinking, functioning or constraints, align on a desired future state for the homelessness response system
Primary work completed by: Nov 1st
PATH TO FUTURE STATE
Develop future statements to serve as an anchor for strategies and actions
#3
Primary work completed by: Dec 1st
Create strategies, initiatives and action steps to move from current state to future state

## Slide 5
City of La Crosse & La Crosse County
1.
Select
a Design Process
2.
Create
a Stakeholder Engagement Blueprint
3.
Implement
Design Process & Engagement Blueprint
4.
Draft
a Written 5-Year Homelessness Response Plan*
Creating a Long-Term Homelessness Response Plan Covering the City of La Crosse
5.
Prepare
a Presentation & Communication Blueprint
PLANNING PHASE: COORDINATION & KEY MILESTONES
Key Milestones
Coordination
City / County Coordinating Team | City / County Coordinating Team
PARTICIPANTS: | Brian Sampson Alexia Krause Andrea Trane Isaac Hoffman Jason Witt
RESOURCES: | Project Management: John Parshall Fiscal Mapping / Analysis: Jen Vote
SCOPE: | - Create & Oversee Project Management Plan - Coordinate Ongoing Workstreams - Troubleshoot Day to Day Issues - Finalize homeless response plan and advance it to the Mayor & County Administrator
* To include recommendations with regards to financing

## Slide 6
City of La Crosse & La Crosse County
Creating a Long-Term Homelessness Response Plan Covering the City of La Crosse
STAKEHOLDER ENGAGEMENT BLUEPRINT
STAKEHOLDER GROUPS
(At least one outreach before December 31st)
Coordinating
Team
Lived Experience
Team
Coulee CoC
CORE SYSTEM WORK TEAMS
(Three engagement sessions prior to December 1st)
Faith Groups
Funders
Final Plan & Recommendations to Mayor and County Administrator
Prevention
Crisis Response
Outflow
Wrap Around
Services
Public / Community
Currently Homeless
County & City Services
Homelessness Agency Leadership
Business
Community
GOALS:
1. Opportunity for contribution
Valued contributions
Transparency
Efficiency
Concrete, actionable result
Housing

## Slide 7
City of La Crosse & La Crosse County
1.
Select
a Design Process
2.
Create
a Stakeholder Engagement Blueprint
3.
Implement
Design Process & Engagement Blueprint
4.
Draft
a Written 5-Year Homelessness Response Plan*
Creating a Long-Term Homelessness Response Plan Covering the City of La Crosse
5.
Prepare
a Presentation & Communication Blueprint
Started
PLANNING PHASE: COORDINATION & KEY MILESTONES
Key Milestones
Coordination
City / County Coordinating Team | City / County Coordinating Team
PARTICIPANTS: | Brian Sampson Alexia Krause Andrea Trane Isaac Hoffman Jason Witt
RESOURCES: | Project Management: John Parshall Fiscal Mapping / Analysis: Jen Vote
SCOPE: | - Create & Oversee Project Management Plan - Coordinate Ongoing Workstreams - Troubleshoot Day to Day Issues - Finalize homeless response plan and advance it to the Mayor & County Administrator
* To include recommendations with regards to financing

## Slide 8
City of La Crosse & La Crosse County
- Project Planning
- Current State Mapping
- Ongoing Coordination
PROJECT STATUS
Work that Has Not Started:
Creating a Long-Term Homelessness Response Plan Covering the City of La Crosse
Work that Has Started:
- Homeless Response System Planning
Work that is About to Start:
- Implementing the Stakeholder Engagement Blueprint

## Slide 9
Interested in joining a work team?
Contact Either:
Brian Sampson, City of La Crosse
sampsonb@cityoflacrosse.org
608-789-8687
or
Isaac Hoffman, La Crosse County
ihoffman@lacrossecounty.org
608-792-1617